## Backlog
Id | Story | Labels | Iteration | Iteration Start | Iteration End | Estimate | Description | Owned By | Task
66492512 | How to: pi | raspberry pi, research | 3 | Mar 4, 2014 | Mar 17, 2014 | 3 | 1 days work together: Henrik + Johan + Simas | Henrik Edholm | • What type of data do you get from the NFC • How to connect NFC • How to connect camera • How to use camera • What datatype for the camera • How to connect HW/SW • Which OS to use? | Which OS to use?
66492778 | Python | raspberry pi, research | 3 | Mar 4, 2014 | Mar 17, 2014 | 3 | Total 3 days of work: Henrik + Johan + Simas | Henrik Edholm | • study syntax
66491484 | How to andriod | mobile app, research | 3 | Mar 4, 2014 | Mar 17, 2014 | 3 | Definition of done: app - 3 days of work - done: (watch a youtube series, tutorials, research other apps how they implement stuff - and practice) | Mikaela Lidström | • developer.andriod.com turtorials • XML – turtorial • Research other apps(Design & Navigation) • Configure SDK & plug-ins(IDE)
66493590 | Google maps | gps location system, mobile app, research | 3 | Mar 4, 2014 | Mar 17, 2014 | 3 | watch a youtube series, tutorials, research other apps how they implement stuff - and practice | Mikaela Lidström | • How to implement on app • Put our icons on map
66931320 | Create basic game design | assassination | 3 | Mar 4, 2014 | Mar 17, 2014 | 3 |  | Henrik Edholm | • Basic layout • Domain model • Sequence diagram
67308596 | Create mobile app | mobile app | 3 | Mar 4, 2014 | Mar 17, 2014 | 3 | Set up the base of the mobile application. | Elsa Wide
66931558 | How to Python (2nd) | raspberry pi, research, server | 4 | Mar 18, 2014 | Mar 31, 2014 | 3 | Know how to pass information from the server to the pi and vice versa, connection to database and one query. | Henrik Edholm | • Connect to database • Run queries (at least one) • Know what type of server we should use
67308748 | Setting up Hub | raspberry pi | 4 | Mar 18, 2014 | Mar 31, 2014 | 3 |  | Henrik Edholm | • Install OS
65449970 | Database structure (sketching) | mobile app, server, website | 4 | Mar 18, 2014 | Mar 31, 2014 | 3 | Sketching of the database structure for the game. | Henrik Edholm | • Assassination parts
66931420 | How to Android (2nd) | gps location system, mobile app, research | 4 | Mar 18, 2014 | Mar 31, 2014 | 5 | Make an app with google maps implemented and a gps location shown | Henrik Edholm | • Make an app • Implement google maps to app • Show GPS location on google maps
65450002 | Setting up NFC-sensor | raspberry pi | 5 | Apr 1, 2014 | Apr 14, 2014 | 5 |  | Johan Nilsson | • Connect to RPi • Test sensor
65450488 | Setting up camera | raspberry pi | 5 | Apr 1, 2014 | Apr 14, 2014 | 1 |  | Johan Nilsson | • Connect camera to RPi • Test camera • Program camera functions
66362304 | Kill target | assassination | 5 | Apr 1, 2014 | Apr 14, 2014 | 3 |  | Simonas Stirbys | • Sequence diagram (White box) • Sequence diagram (Black box) • Use case • Scenarios
66362542 | Integrate map | mobile app | 6 | Apr 15, 2014 | Apr 28, 2014 | 1 |  | Felix Fortoul
65449856 | Setting up GPS system | gps location system | 6 | Apr 15, 2014 | Apr 28, 2014 | 3 |  | Felix Fortoul
69608098 | PivotalTracker basics | research | 6 | Apr 15, 2014 | Apr 28, 2014 | 1 |  | Henrik Edholm | • Henrik explains the basics of PivotalTracker
69607716 | Design UI | mobile app | 6 | Apr 15, 2014 | Apr 28, 2014 | 1 | DoD: The basic app functionality have been designed. | Henrik Edholm | • Sketch all activities • Upload all sketches to Dropbox
69607864 | Design Database | server | 6 | Apr 15, 2014 | Apr 28, 2014 | 3 |  | Henrik Edholm | • Tables to use • Datatypes to use • Sketch tables
69607776 | Extend classdiagram | mobile app | 6 | Apr 15, 2014 | Apr 28, 2014 | 1 | DoD: Extend the current classdiagram so it covers this sprint | Mikaela Lidström | • Assign Target • Retrieve Position
69607890 | Server research | mobile app, research | 6 | Apr 15, 2014 | Apr 28, 2014 | 5 | DoD: The information learnt is documented (with links) | Simonas Stirbys | • What functionality do we need • What type of server
69607850 | Android Research (3) | mobile app, research | 6 | Apr 15, 2014 | Apr 28, 2014 | 3 | DoD: This is done when we have the knowledge of how to connect the app to the server. | Johan Nilsson | • Research server connectivity • Database connectivity
68697574 | Set up App Server | mobile app, server | 6 | Apr 15, 2014 | Apr 28, 2014 | 5 | Add the database, connect to android app and raspberry pi. | Henrik Edholm | • connect to application • connect to raspberry pi • add database
69609474 | Creating file server | server | 6 | Apr 15, 2014 | Apr 28, 2014 | 1 | DoD: Upload and access files | Johan Nilsson | • Decide server • Upload files • Extract files
69607090 | Register account | mobile app, server | 6 | Apr 15, 2014 | Apr 28, 2014 | 1 | DoD: A user can register and their information is saved on the database. | Johan Nilsson | • Register Account
69607478 | Login to app | mobile app, server | 6 | Apr 15, 2014 | Apr 28, 2014 | 1 | DoD: User can use his/her account to login to the app | Johan Nilsson | • Log In • Log Out
69607742 | Setup Database | server | 6 | Apr 15, 2014 | Apr 28, 2014 | 1 | DoD: We get the results we want from the scripts. | Johan Nilsson | • Create scripts • Run scripts • Testing database
69608018 | GitHub lecture/education | research | 7 | Apr 29, 2014 | May 12, 2014 | 3 | DoD: Everyone knows how to use GitHub in a proper way. | David M Szabo | • Lecture by John
66362778 | Profile page | mobile app, website | 7 | Apr 29, 2014 | May 12, 2014 | 1 |  | Mikaela Lidström | • View statistics • View items • View account info
70427874 | Configurate Xperia | mobile app | 7 | Apr 29, 2014 | May 12, 2014 |  | Configurating Felix's old Sony Xperia for android development | Simonas Stirbys | • Install mod • Install newer OS
67286432 | Overview statistics | assassination | 7 | Apr 29, 2014 | May 12, 2014 | 3 | Users are able to see how many they killed and the amount of times they died. | Mikaela Lidström
66362322 | Use item | assassination | 7 | Apr 29, 2014 | May 12, 2014 | 3 |  | Mikaela Lidström
66362260 | Acquire target | assassination, mobile app | 7 | Apr 29, 2014 | May 12, 2014 | 3 | This user story covers how the users get their targets. | Johan Nilsson | • Retrieve Position • Assign Target
66362418 | Friend list | mobile app, server | 7 | Apr 29, 2014 | May 12, 2014 | 3 |  | Simonas Stirbys | • Fill up list with "friends" • Availability to select friend
66369490 | Link phone | mobile app, raspberry pi, server | 7 | Apr 29, 2014 | May 12, 2014 | 3 |  | Johan Nilsson
70426784 | Change profile picture | raspberry pi, server | 7 | Apr 29, 2014 | May 12, 2014 | 1 |  | Johan Nilsson
66369654 | Add friend | mobile app, server | 7 | Apr 29, 2014 | May 12, 2014 | 3 |  | Simonas Stirbys
70426552 | Design Graphics | mobile app | 7 | Apr 29, 2014 | May 12, 2014 | 5 | Graphical design for game items and app icon | Felix Fortoul | • app icon • Naegling – Sword • Blowgun • Strangling Wire • Odjobs Hat • Poking Stick • The Immovable Object – Shield • AWP - sniper rifle • Good Judgement – Mind • Chastitybelt • Draconic Armour • Ring of Absorbation • Bandaid
71304652 | Accept/deny friend request | mobile app, server | 8 | May 13, 2014 | May 26, 2014 | 3 |  | Elsa Wide
71305050 | Reset password | mobile app, server | 8 | May 13, 2014 | May 26, 2014 | 1 |  | Johan Nilsson
71304702 | Update registration | mobile app, server | 8 | May 13, 2014 | May 26, 2014 | 1 |  | Johan Nilsson
70426802 | Assassinate target | mobile app, server | 8 | May 13, 2014 | May 26, 2014 | 3 |  | Mikaela Lidström
67286382 | Get ranked | assassination, mobile app | 8 | May 13, 2014 | May 26, 2014 | 1 | Users get ranked based on their K/D ratio | Mikaela Lidström
71305042 | Restrict username & friends | mobile app, server | 8 | May 13, 2014 | May 26, 2014 | 1 |  | Johan Nilsson
67193522 | Collect item from hub | assassination, raspberry pi | 8 | May 13, 2014 | May 26, 2014 | 3 | This user story is specifically about collecting items from the hub (Raspberry Pi) | Johan Nilsson | • Sequence diagram (White box) • Sequence diagram (Black box) • Use cases • Scenarios
71304740 | Show online friends | mobile app | 8 | May 13, 2014 | May 26, 2014 | 1 |  | Elsa Wide
71304626 | Code optimization | mobile app, raspberry pi, server | 8 | May 13, 2014 | May 26, 2014 |  |  | Mikaela Lidström
66931236 | Create design document |  | 8 | May 13, 2014 | May 26, 2014 | 5 | 4+1 architectural view model | Felix Fortoul | • Class diagram • Communication diagram • Sequence diagram • Component diagram • Package diagram • Activity diagram • Deployment diagram • Use cases • Scenarios • Initial Update 5
71247898 | Final Report |  | 8 | May 13, 2014 | May 26, 2014 | 3 |  | David M Szabo
71304528 | GFX for Sprint 6 |  | 8 | May 13, 2014 | May 26, 2014 | 1 |  | Felix Fortoul | • Default profile pic • App icon
71304588 | Meeting log and time sheet |  | 8 | May 13, 2014 | May 26, 2014 | 1 |  | Henrik Edholm
71305022 | Quality Documentation |  | 8 | May 13, 2014 | May 26, 2014 | 1 | Includes bugtracking | Mikaela Lidström
68695884 | Final |  | 8 | May 13, 2014 | May 26, 2014 |  | This is the release item with a deadline of the 28th of may
Note on J1: Simonas: Double click a row to expand